# ASSAY — Project Planning Document

Agentic SOV Cleansing & Intelligence System · Adrosonic Build Hackathon

Sep 29, 2026 · @Ri

## 1. Document control and purpose

This plan tells a 4-person team exactly what to build, who builds it, and in what order, so that ASSAY runs end-to-end on all 3 test SOVs within the 24-hour window. It pairs with the ASSAY SRS, which defines what the system must do; this document defines how the team delivers it.

| Version | Change | Author |
| --- | --- | --- |
| 0.1 | First draft, aligned to the Round 1 proposal | Team lead |

Open question: hackathon start date and time are not yet confirmed; all hours below are relative to the start (H+0).

## 2. Project overview

ASSAY turns a messy client Statement of Values (SOV) into a schema-conformant Cleaned_SOV.xlsx through four collaborating agents and a human approval gate. Its design stance is "the LLM proposes, code disposes": the model adjudicates and explains, while every change to data is a deterministic, human-approved operation.

Problem. SOVs arrive in inconsistent formats (multi-sheet, shifted headers, merged banners, abbreviations, placeholders). Manual cleansing takes hours per file and reaches 53% header-mapping accuracy.

Objectives (all five are must-haves for full scoring):

- Ingest .xlsx/.csv, find the data sheet and header row automatically.

- Map raw headers to the 17 target fields with confidence-scored JSON.

- Detect missing values, type errors, logical errors and format inconsistencies.

- Explain every mapping and every issue in plain English, including uncertainty.

- Apply changes only after human approval; export Cleaned_SOV.xlsx and Audit_Log.xlsx.

Success criteria (evaluation weights in brackets):

| Criterion | Spec target | Team target |
| --- | --- | --- |
| Mapping accuracy (20%) | ≥ 74% | ≥ 85% on mutation harness |
| Data quality detection (15%) | ≥ 90% recall | ≥ 95% on planted anomalies |
| Transformation correctness (15%) | ≥ 95% rows | 100% of approved ops applied deterministically |
| Agentic design quality (20%) | 4 distinct agents, shared state | 4 LangGraph nodes, typed state, contract gates |
| Explainability (15%) | 100% rationale | 100%, enforced by schema |
| Human-in-the-loop UX (10%) | Non-technical reviewer can act | Review cards, before/after grid, export lock |
| Innovation and bonus (5%) | Any bonus item | Vector memory, live agent graph, re-reasoning, intake quality score |

## 3. Scope and deliverables

The minimum bar is a working end-to-end pipeline on all 3 test SOVs with 4 distinct agents; everything else is ranked behind it.

In scope (must-have): file upload (.xlsx, .csv, up to 5,000 rows), sheet and header detection, 17-field mapping, anomaly detection, LLM-generated rationale, human review UI, deterministic transformation, Cleaned_SOV.xlsx, Audit_Log.xlsx, processing summary.

In scope (bonus, only after must-haves pass): vector memory of past mappings, live agent graph, re-reasoning on rejection, intake data-quality score.

Out of scope: user accounts and login, multi-user concurrency, cloud deployment, formats other than .xlsx/.csv, geocoding or address validation against external services, any automatic fixing without approval.

| Deliverable | Format | Owner | Needed for |
| --- | --- | --- | --- |
| Running application | Docker Compose, one command | Member D | Demo, all criteria |
| Source code + README | Git repository | Team lead | Agentic design, reproducibility |
| Cleaned output for each sample | Cleaned_SOV.xlsx | Member C | Transformation correctness |
| Audit log for each sample | Audit_Log.xlsx | Member C | Audit completeness (NFR-3) |
| Mapping JSON for each sample | JSON | Member B | Mapping accuracy, demo stage 2 |
| Harness accuracy report | Markdown | Member B | Evidence for mapping and recall targets |
| 10-minute demo | Live + backup recording | Team lead | All 7 demo stages |

## 4. Team structure and roles

Each member owns one vertical slice end-to-end, and the team lead owns the shared state contract and integration, so no two people edit the same module.

| Role | Owns | Key skills |
| --- | --- | --- |
| Team lead: orchestration and integration | LangGraph graph, SOVState contract, contract gates, FastAPI, Docker, demo | Backend architecture, Python |
| Member A: ingestion and Agent 1 | File loader, merged-header handling, header-row scoring, sheet ranking | pandas, openpyxl |
| Member B: Agent 2 and evaluation | Three evidence channels, score matrix, Hungarian solver, LLM adjudicator, mutation harness | RapidFuzz, embeddings, SciPy |
| Member C: Agents 3 and 4 | Pandera rules, transformation DSL, executor, audit log, output self-check | Data validation, openpyxl |
| Member D: review UI | Angular review screens, before/after grid, SSE agent graph, export gate | Angular, TypeScript |

With 4 people, the team lead also takes Member D's role or Member A's role; Agent 1 is the smallest slice and is the natural one to combine.

RACI (R = does it, A = signs off, C = consulted, I = informed):

| Activity | Lead | A | B | C | D |
| --- | --- | --- | --- | --- | --- |
| State schema and gates | A/R | C | C | C | I |
| Sheet and header detection | A | R | I | I | I |
| Schema mapping | A | I | R | C | I |
| Quality rules and DSL | A | I | C | R | I |
| Review UI | A | I | I | C | R |
| LLM prompts and guardrails | A | I | R | R | I |
| Harness and accuracy report | C | C | R | C | I |
| Demo and pitch | R | C | C | C | C |

## 5. Work breakdown structure

The build splits into 7 workstreams and 34 tasks; P0 tasks make the end-to-end pipeline work, P1 tasks earn score above the bar, P2 tasks are bonus.

| ID | Task | Owner | Est. (h) | Priority | Depends on |
| --- | --- | --- | --- | --- | --- |
| 1.1 | SOVState Pydantic models and contract gates | Lead | 1.5 | P0 | – |
| 1.2 | LangGraph skeleton with 4 stub agents + interrupt | Lead | 1.5 | P0 | 1.1 |
| 1.3 | FastAPI endpoints: upload, run, decisions, export | Lead | 2 | P0 | 1.2 |
| 1.4 | SSE stream of agent events | Lead | 1 | P1 | 1.3 |
| 1.5 | Docker Compose and README | Lead | 1 | P0 | 1.3 |
| 2.1 | Loader for .xlsx/.csv with size and type pre-checks | A | 1 | P0 | 1.1 |
| 2.2 | Merged-cell forward-fill and composite banner headers | A | 2 | P0 | 2.1 |
| 2.3 | Header-row scoring (string density, type consistency below) | A | 2 | P0 | 2.1 |
| 2.4 | Sheet scoring and Primary/Secondary/Reject manifest | A | 1.5 | P0 | 2.3 |
| 2.5 | Totals and subtotal row detection | A | 1 | P1 | 2.3 |
| 3.1 | Target field catalogue: 17 fields, descriptions, glossary | B | 1 | P0 | – |
| 3.2 | Lexical channel: exact + RapidFuzz after glossary expansion | B | 1.5 | P0 | 3.1 |
| 3.3 | Semantic channel: bge-small embeddings | B | 1.5 | P0 | 3.1 |
| 3.4 | Value-fingerprint channel | B | 2 | P0 | 2.1 |
| 3.5 | Score fusion and Hungarian assignment, margin confidence | B | 1.5 | P0 | 3.2–3.4 |
| 3.6 | LLM adjudicator with enum output and evidence verifier | B | 2 | P1 | 3.5 |
| 3.7 | Mutation harness and accuracy report | B | 2.5 | P1 | 3.5 |
| 3.8 | Vector memory (Chroma) with negatives | B | 1.5 | P2 | 3.5 |
| 4.1 | Pandera schema: types, ranges, allowed values | C | 1.5 | P0 | 3.1 |
| 4.2 | Logical and cross-field rules (placeholders, zip vs state, TIV reconciliation) | C | 2 | P1 | 4.1 |
| 4.3 | Completeness and intake quality score | C | 1 | P0 | 4.1 |
| 4.4 | Transformation DSL (~10 ops) with before/after preview | C | 2 | P0 | 4.1 |
| 4.5 | LLM rationale, op selection, re-reasoning on rejection | C | 2 | P0 | 4.4 |
| 5.1 | Executor applying approved ops on a copy | C | 1.5 | P0 | 4.4 |
| 5.2 | Audit log writer, one entry per changed cell | C | 1 | P0 | 5.1 |
| 5.3 | Excel writer and output self-validation | C | 1 | P0 | 5.1 |
| 6.1 | Angular shell, upload screen, run status | D | 1.5 | P0 | 1.3 |
| 6.2 | Sheet manifest and mapping review cards | D | 2.5 | P0 | 6.1 |
| 6.3 | Issue review cards with before/after grid | D | 2.5 | P0 | 6.2 |
| 6.4 | Accept / reject-with-note / edit, approve-all ≥ 0.90, export lock | D | 2 | P0 | 6.3 |
| 6.5 | Live agent graph | D | 1.5 | P2 | 1.4 |
| 7.1 | End-to-end run on 3 samples, fix defects | All | 3 | P0 | all P0 |
| 7.2 | Demo script, backup recording, rehearsal | Lead | 2 | P0 | 7.1 |
| 7.3 | Final README, repo clean-up, key check | Lead | 0.5 | P0 | 7.1 |

## 6. Pre-hackathon preparation

Preparation removes setup and learning time so all 24 hours go to building. Confirm the rules first: if pre-written solution code is not allowed, prepare only environments, notes and throwaway spikes.

Environment (everyone):

- ☐ Python 3.11, Node 20, Angular CLI, Docker Desktop installed and tested

- ☐ Shared Git repository created, branch rules agreed (section 8)

- ☐ LLM API key obtained and stored in each machine's environment, never in code

- ☐ bge-small model downloaded once and cached (avoids venue Wi-Fi risk)

- ☐ Ollama with a small local model installed as the offline fallback

Knowledge (owner in brackets):

- ☐ LangGraph StateGraph, interrupt() and checkpointer spike (Lead)

- ☐ openpyxl merged-cell reading on a sample workbook (A)

- ☐ RapidFuzz scorers and scipy.optimize.linear_sum_assignment spike (B)

- ☐ Pandera DataFrame schema and custom checks spike (C)

- ☐ Angular SSE consumption and a data-grid component chosen (D)

Domain assets:

- ☐ Insurance abbreviation glossary: at least 60 entries (Bldg, Repl, Cont, BI/EE, Const, Occ, Yr Blt, Sq Ft, Sprk, Prot, TIV)

- ☐ Construction and occupancy vocabularies (ISO classes 1–6, common occupancy terms)

- ☐ US state names and 2-letter codes; states whose zips start with 0

- ☐ 3–5 practice SOVs built by hand with realistic mess, for the harness

Agreements:

- ☐ SOVState field names and JSON shapes agreed on paper before H+0

- ☐ UI wireframe for review cards sketched and agreed

## 7. 24-hour execution schedule

The graph runs on stub agents by hour 3, so every member builds against a working pipeline instead of integrating at the end. Hour 12 is the critical gate: if sample 1 does not clean end-to-end by then, all P1 and P2 work stops until it does.

24-hour plan · 6 lanes, 5 gates

Gate rules:

- A gate is passed only when the whole team has watched it work on screen.

- A missed gate triggers the fallback for that gate in the risk register (section 10), not extra hours.

- After G4 (hour 20), no new features: only bug fixes, README and demo preparation.

- Each member takes one 60–90 minute sleep or rest break, staggered so no lane is empty for long; the team lead rests after G3.

## 8. Integration and engineering practices

Integration risk is removed by agreeing the state contract before H+0 and merging small changes to main every 1–2 hours.

Repository layout:

assay/
  backend/
    state/        # SOVState models, contract gates (Lead)
    agents/
      sheet_intel/   # Agent 1 (A)
      mapping/       # Agent 2 (B)
      quality/       # Agent 3 (C)
      transform/     # Agent 4 (C)
    llm/          # prompts, schemas, evidence verifier (B, C)
    api/          # FastAPI routes, SSE (Lead)
    harness/      # mutation generator, scoring (B)
  frontend/       # Angular review UI (D)
  samples/        # 3 test SOVs + practice files
  docker-compose.yml
  README.md

Working rules:

- One short-lived branch per task ID from section 5 (for example feat/3.5-solver); merge to main after a second member reads the diff for 5 minutes.

- main must always run end-to-end; a merge that breaks the stub pipeline is reverted immediately, not fixed forward.

- Each agent is a pure function of SOVState in and a partial state out; agents never import each other.

- Changing a SOVState field needs the team lead's approval and a message in the team channel.

- Every LLM call goes through one wrapper in llm/ that logs prompt, response, latency and validation result.

- No API key in code or Git: .env files are in .gitignore, and .env.example lists the variable names.

- Deterministic seeds for embeddings and sampling so the same file gives the same result on every run.

## 9. Testing and evaluation plan

The team measures its own scores before the judges do: a mutation harness turns the 3 samples and the practice files into a few hundred labelled variants.

Mutation harness. Starting from a file whose correct mapping is known, it generates variants by abbreviating or misspelling headers, shuffling column order, inserting blank or title rows above the header, adding a notes sheet, merging a banner row, and planting anomalies (negative values, future years, placeholders, currency strings, 4-digit zips, full state names, duplicate rows). Every change is recorded, so accuracy and recall are computed, not estimated.

| Test level | What it checks | Owner | When |
| --- | --- | --- | --- |
| Unit | Each DSL op, each quality rule, header scoring, solver | Each owner | With every task |
| Contract | Each gate rejects malformed state | Lead | From H+3 |
| End-to-end | Upload to export on each of the 3 samples | Lead | From G2, every 2 hours |
| Harness | Mapping accuracy, anomaly recall | B | From H+15, every run logged |
| Output conformance | 17 columns in order, types, no merges, blanks not zeros, file and sheet names | C | Every export |
| Robustness | Empty file, wrong extension, password-protected file, 6,000 rows, no header at all | A | H+16 to H+19 |
| UI walkthrough | A person who did not build the UI completes a review | D + one other member | H+18 |

Acceptance thresholds before G4: mapping accuracy ≥ 80% on the harness, anomaly recall ≥ 90%, all 3 samples export without error, and zero changes in the output that do not appear in the audit log.

## 10. Risk register

The biggest risk is late integration, which is why the skeleton is built first; every other risk has a fallback that keeps the demo working.

| ID | Risk | Likelihood | Impact | Mitigation | Fallback | Owner |
| --- | --- | --- | --- | --- | --- | --- |
| R1 | Agents do not integrate until late | Medium | High | Stub graph at H+3, merge every 1–2 h | Cut P2 items at G2 | Lead |
| R2 | Real test SOVs differ from expectations (layout, headers) | High | High | Run all 3 samples through Agent 1 in the first hour after release | Manual sheet and header override in UI | A |
| R3 | Mapping accuracy below 74% | Medium | High | Value fingerprints, glossary, harness tuning from H+15 | Raise the review threshold so more columns go to the human | B |
| R4 | LLM API slow, rate-limited or down at the venue | Medium | Medium | Timeouts and retries in the wrapper; LLM called per column, not per row | Ollama local model; templated rationale from rule metadata | B, C |
| R5 | LLM returns invalid or invented output | Medium | High | Enum-constrained schema, evidence verifier | Discard and send to human review | B |
| R6 | Venue Wi-Fi fails | Medium | Medium | Model weights and Docker images cached before the event | Mobile hotspot; offline demo recording | Lead |
| R7 | Angular UI takes longer than planned | Medium | High | Build review cards first, graph last | Minimal review table; drop the live graph | D |
| R8 | Merged cells or multi-row headers break the loader | Medium | Medium | openpyxl merge map, unit tests on crafted files | Treat banner row as a separate header and flag it | A |
| R9 | Export fails schema check on a sample | Low | High | Self-check after every export from G2 | Fix the op, not the output file | C |
| R10 | Team fatigue after hour 16 | High | Medium | Staggered rest breaks, freeze at H+20 | Lead presents; one member drives the demo | Lead |
| R11 | Live demo fails on stage | Low | High | Rehearse twice; restart script ready | Backup screen recording of the full run | Lead |

## 11. Demo plan (10 minutes)

The demo follows the judges' 7-stage checklist in order, uses Sample 3 (multi-sheet, missing columns) for the live run, and shows Sample 2's semantic matches as pre-run evidence.

| Time | Stage | What is shown | Presenter |
| --- | --- | --- | --- |
| 0:00–0:45 | Opening | The problem in one sentence; "the LLM proposes, code disposes"; architecture slide | Lead |
| 0:45–1:45 | 1. Upload and sheet detection | Sample 3 uploaded; manifest ranks sheets with reasons; header row found below a title block | Lead |
| 1:45–3:00 | 2. Schema mapping | Mapping JSON with confidence and method; one semantic match ("Bldg Repl Cost" → Building Value); one low-margin column showing its runner-up | B |
| 3:00–4:00 | 3. Data quality report | Per-field completeness; at least 3 flagged issues of different types (placeholder year, 4-digit zip vs state, currency in a value column) | C |
| 4:00–5:00 | 4. Recommendations | Queue with one column mapping, one data correction, one standardisation, each with rationale and uncertainty | C |
| 5:00–6:45 | 5. Human approval | Approve-all ≥ 0.90; accept one item; reject one with a note and show the agent re-reason live; export button locked until done | D |
| 6:45–7:45 | 6. Transformation and audit | Cleaned preview beside the audit log entries | C |
| 7:45–8:45 | 7. Download and conformance | Open Cleaned_SOV.xlsx: 17 headers, types, no merges; self-check result shown | D |
| 8:45–10:00 | Close | Harness accuracy vs 74% target; live agent graph; memory recall on a second upload | Lead |

Preparation: the backup recording of this exact run is saved locally and on a USB drive before G5.

## 12. Communication and definition of done

The team runs a 5-minute stand-up at every gate and uses one chat channel for all decisions, so nothing important lives only in someone's head.

Stand-up at each gate: what passed, what is blocked, whether any P1/P2 item is cut. The team lead records decisions in this document.

A task is done when:

- ☐ It is merged to main and the end-to-end run still passes

- ☐ It has at least one unit test, or a harness case for mapping and quality logic

- ☐ Every decision it makes carries a rationale string

- ☐ It writes nothing to data without an approved decision and an audit entry

- ☐ Its owner has shown it working to one other member

The project is done when:

- ☐ All 3 samples produce Cleaned_SOV.xlsx and Audit_Log.xlsx that pass the self-check

- ☐ All 7 demo stages run without manual workarounds

- ☐ README lets a stranger run the app with one command

- ☐ No API key appears anywhere in the repository history

- ☐ Demo rehearsed twice and backup recording saved